## Slide 1
PRODUCTION PLAN · v1.0 · AUGUST 2026
From working application
to internal SaaS platform
Taking the multi-tenant NER platform to production for InApp's clients — and folding in the architecture and use cases proven by InApp's existing RAG chatbots.
5 phases
~9 months
3 developers
no DevOps / QA / security
~$1.9-2.6k
monthly infra at 10-15 tenants
Notes: Plan document: docs/production-plan.md. Product decision: NER/document-intelligence platform that also hosts chatbots. Existing chatbots are re-implemented natively, not ported as code or plugins.

## Slide 2
WHERE WE ARE TODAY
A working application that has never been deployed
What already works
Nine FastAPI services + Next.js portal, all functional
Schema-per-tenant isolation from a tenant_template blueprint
Deterministic LangGraph chat routing — state-driven, never LLM-chosen
Full lifecycle: upload, OCR, annotate, fine-tune, promote, extract, chat
Feature flags, hashed widget API keys, audit logging, quota columns
What blocks production
docker-compose only — deploy/k8s holds MLflow alone
Zero observability: no prometheus, opentelemetry or structlog in src/
Rate limiter is an in-process dict — limits multiply per replica
No LLM token accounting, so no cost attribution or enforcement
Single Postgres, no pooler, no replica, no HA, no backups
Secrets in .env; no SSO; no load, security or chaos testing
Notes: The gaps are not defects in the application — they are the difference between an application and a platform.

## Slide 3
DEFINITION OF PRODUCTION
Four things must become true
1
Anything can be swapped by config
Retrieval and generation are hardwired into a fixed graph topology. Swapping a model, retriever or agent today means editing code and redeploying.
2
One tenant cannot degrade another
In-process rate limits, per-pod model cache, one shared Celery pool, one unpooled Postgres. Nothing enforces fair use.
3
Every tenant's consumption is visible and enforced
No metrics, traces or logs. Token spend is invisible. Quota columns exist on public.tenants but nothing reads them.
4
It survives a node failure and a security review
No Kubernetes manifests, no HA, no backups, no SSO, no penetration test.
Notes: None of the four is true today. Each maps to a phase in the roadmap.

## Slide 4
DECISIONS LOCKED
Scope confirmed, and scope deferred
Confirmed — not revisited
NER platform that also hosts chatbots — training and annotation stay core
Existing chatbots re-implemented natively; no code lift, no data migration
Our own documents only — no external data connectors
Agent switching is config-driven and platform-team-only
Four existing roles are sufficient; no document-level ACLs
SSO required · hard quota enforcement · per-tenant metering
Azure, single region, shared multi-tenant · Postgres + pgvector
Deferred to a later phase
Pricing and licensing model
Branding and white-labelling
Compliance certification and published SLA
Multi-region and dedicated deployments
Beta cohort selection
Assumed, because no answer was available
Azure OpenAI as provider — gpt-4o + gpt-4o-mini
Training on an on-demand GPU spot VM (~$30/month)
Year one: 10-15 tenants, ~200 users, ~50k messages/month
Central India region; SOC 2 controls respected but not certified
Each assumption names a phase by which it can be reversed cheaply.

## Slide 5
TARGET ARCHITECTURE
Three planes, cleanly separated
CONTROL PLANE
NEW BUILD
Identity · entitlements · quotas · metering · observability
Every request passes through it. Nothing bypasses it.
CAPABILITY PLANE
REFACTOR
Agents · retrievers · tools · LLM adapters · rerankers
All resolved from a registry at request time. All swappable.
DATA PLANE
HARDEN
Postgres + pgvector · Blob · Redis · RabbitMQ · model artifacts
Per-tenant schemas, per-tier resource pools.
The one change that makes everything else possible: a capability never touches infrastructure directly and never reads config from the environment. It receives a TenantContext carrying resolved configuration, the metering handle, and the budget remaining.

## Slide 6
MAKING IT FUTURISTIC
Swapping a component is a config change
A
Narrow protocols
Retriever, LLMAdapter, Tool and Agent protocols in src/shared/capabilities. Existing sql_generator, embedding_service, entity_resolver and reranker already fit these shapes.
B
A registry, plus config
Named implementations resolved at request time. Capability profiles in versioned YAML, with per-tenant overrides — today's boolean flags, one level up.
C
Topology becomes data
The graph is compiled from the resolved profile instead of hardcoded. Routing predicates stay pure functions of state — never LLM-chosen. That invariant is why the pipeline is testable.
D
Versioned and reversible
Profile changes are git commits, stamped on every conversation record. Any answer traces to the exact configuration that produced it. Rollback is a revert.
Out of scope by decision: no tenant-facing agent builder, no plugin marketplace, no MCP server — but Tool.schema is MCP-shaped, so adopting MCP later is an adapter, not a redesign.

## Slide 7
CHATBOT PARITY
What the existing chatbots do that we do not
FROM FASTGRAPHRAG
Graph-RAG retrieval
Today retrieval is three flat parallel lookups. Graph-RAG follows edges between entities to answer questions no single chunk contains.
Build tenant_{id}.entity_graph_edges from extracted_entities co-occurrence; register a graph_walk retriever. Purely additive — a fourth entry in the retrievers list.
OVER EXTRACTED DATA
Chart plotting
Business users want the answer plotted, not narrated.
A chart_agent returning a Vega-Lite specification — never rendered images and never executable code. Data access via the existing read-only SQL role.
BEYOND OCR
Multi-format ingestion
Today: Tesseract on images and PDFs only.
Format-handler registry keyed on MIME type: DOCX, XLSX/CSV, PPTX, HTML, EML, plus a native-text PDF fast path that skips OCR entirely — a large accuracy and cost win.
Porting method. Sit with each chatbot's owner and capture behaviour as 15-30 golden question/answer pairs plus prompts and retrieval strategy. Express it as a capability profile, run the golden set, iterate until it passes. The golden sets become permanent regression tests — the only reliable proof that a re-implementation matches a system whose code we are not reusing.

## Slide 8
NOISY NEIGHBOURS
Six contention points already in the code
1
LLM concurrency and spend
One tenant's batch run consumes the whole Azure OpenAI TPM quota.
Shared LLM broker · Redis token buckets per tenant · separate interactive and batch deployments · hard budgets returning HTTP 402
2
Postgres
One unpooled instance. Schema-per-tenant isolates data, not load.
Flexible Server with zone-redundant HA · mandatory PgBouncer · statement timeouts by workload class · read replica for analytics · HNSW indexes
3
model_serving memory
2 GB in-process cache per pod means every pod loads every hot tenant's model.
Consistent-hash routing by tenant_id · per-tenant cache reservation · dedicated pools as a future premium tier
4
Celery workers
Global FIFO. One tenant's 50-document batch starves everyone.
Queue per workload class · per-tenant concurrency semaphore · weighted fair queueing · training on ephemeral GPU nodes · KEDA autoscaling
5
Storage and ingestion
max_storage_gb is a column nobody checks; OCR is unbounded.
Enforce at upload with 402 · page and size caps · OCR admission control · native-text PDF fast path removes most OCR load
6
The rate limiter itself
Process-local dict: effective limit is limit x replica count, and buckets never reap.
Redis sliding window in src/shared, applied at the gateway for every service — not just chat_api. Keep the X-RateLimit-* header contract
Notes: Ordered by how quickly each will bite in production. LLM spend is first because nothing in the code accounts for tokens at all today.

## Slide 9
SCALABILITY AND HIGH AVAILABILITY
Scale out, and survive failure
How each layer scales
Stateless services — HPA on CPU and p95 latency, 2 to 10 replicas
model_serving — HPA 2 to 8, consistent-hash routed, memory node pool
Celery — KEDA on per-queue depth, 0 to 20 workers
GPU training — ephemeral spot pool, scales to zero
Postgres — vertical, then read replicas, then tenant-group sharding
Availability targets
Zone failure — AKS across 3 zones; zone-redundant Postgres and Redis
Pod failure — 2+ replicas of everything, PDBs, probes on all nine services
Data loss — RPO 15 min, RTO 4 hours, with quarterly restore drills
Deploy failure — rolling updates, helm rollback, expand-contract migrations
Azure OpenAI outage — circuit breaker returns retrieved evidence unsynthesised rather than erroring
Two commitments worth stating plainly. Because multi-region is deferred, this plan commits to no external SLA — we target 99.5% internally, which single-region zone-redundant AKS supports. And an untested backup is not a backup: the restore drill is a deliverable, not a nice-to-have.

## Slide 10
CONTROL LAYER
The layer that turns an application into a platform
Identity and access
Entra ID via OIDC, with per-tenant IdP federation. Short-lived tokens plus Redis refresh, enabling session revocation — impossible today. Service auth on /internal/v1/*, currently unauthenticated.
Metering
public.usage_events, partitioned monthly, written asynchronously so metering never adds latency. Tokens, embeddings, messages, pages, GPU-minutes, storage, API calls.
Entitlements and quotas
plan_code plus plan_entitlements. One check_entitlement / consume_quota pair called from every enforcement point. Hard 402 with a structured body naming the limit and reset time.
Observability
structlog with tenant, user and trace ids. OpenTelemetry across all nine services — wire the existing _traced decorator in nodes.py to real spans. Prometheus RED plus token spend, all labelled by tenant.
Metering is visibility-only for now — but recorded at per-user and per-conversation grain, because that costs nothing extra today and cannot be reconstructed later.

## Slide 11
MONETIZATION AND LICENSING
Build the meter now, set the price later
Built now
Accurate, durable per-tenant usage records
A real, enforced plan and entitlement model
cost_estimate_usd on every LLM call — gross margin per tenant visible from day one
Exportable monthly usage statement per tenant
Deliberately not built
Payment processing and invoicing
Subscription lifecycle and dunning
License keys and trial management
No billing provider is selected, and building against an unchosen provider is waste.
Recommendation for the pricing phase
Token spend dominates marginal cost and varies roughly tenfold between tenants doing chat versus batch extraction, so a pure per-seat model will lose money on heavy users. A base platform fee per tenant plus metered usage above an included allowance matches cost to revenue. The metering built here supports either model — which is the point of building it first.

## Slide 12
SECURITY BASELINE
The minimum for a platform holding clients' documents
Secrets and transport
Key Vault with workload identity — all secrets out of .env, and NER_OPENAI_API_KEY rotated since it has lived in plaintext. TLS everywhere including intra-cluster, Front Door plus WAF at the edge.
Tenant isolation, proven
An automated test asserting cross-tenant access returns 403/404 for every endpoint, generated from the OpenAPI spec so a new endpoint cannot skip it. Any leak fails the build.
Prompt injection
Uploaded documents are attacker-controlled text entering the prompt — the highest-risk vector here. Input scanning, output citation enforcement, and the hard rule that no LLM output is ever executed.
Generated SQL
Read-only role, per-tenant schema scoping, statement timeouts, query cost ceiling, no DDL or DML grants. The chart agent returns a specification, never code.
With no security staff and three junior developers, one external penetration test before general availability is a requirement, not a nice-to-have. Budget $5-10k. Everything else above is achievable in-house.

## Slide 13
TESTING FOR PRODUCTION
Automated gates instead of a QA team
Gates on every pull request
Unit — 70% on changed lines, 85% on control-layer code in src/shared
Contract — OpenAPI diffs across all nine services; breaking change fails
Integration — real Postgres, Redis and MinIO via testcontainers, full flow
Tenant isolation — generated from OpenAPI; any leak is blocking
Golden-set evaluation — regression below baseline blocks a profile change
Security — bandit, semgrep, Trivy, gitleaks, pip-audit
Pre-release campaigns
Load — k6 and Locust against a production-shaped staging environment
Chaos — kill pods under load, fail over Postgres, block Azure OpenAI, exhaust a quota mid-conversation
LLM security — OWASP LLM Top 10, including injection through uploaded document content
DAST — OWASP ZAP weekly against staging
External penetration test before GA
Beta — internal alpha 4 weeks, then 2-3 clients for 8 weeks
Environments today: local and CI only. A production-shaped staging environment is a Phase 1-2 deliverable — without it there is nowhere safe to run load or chaos tests.

## Slide 14
LOAD AND PERFORMANCE
Load targets, and the test that matters most
30
concurrent conversations sustained
p95 first token under 2.5s
100
concurrent in a 5-minute burst
no 5xx, graceful 429
500
documents batch-extracted
within 30 min, chat p95 intact
24h
soak at 50% load
no memory growth, no leaks
THE ACCEPTANCE TEST FOR THE ENTIRE MULTI-TENANCY WORKSTREAM
One tenant at ten times its quota must not move another tenant's p95 by 20%.
This is the difference between an application and a SaaS platform — and it is the test that would fail today.
Derived from the year-one scale assumption — roughly 10-15 tenants, 200 users, 50k messages per month — with three times headroom. Throughput runs use a stubbed LLM; a smaller run uses live Azure OpenAI for realistic latency. Confirming the real scale expectation would let us tighten these.

## Slide 15
ROADMAP
Five phases, roughly nine months, three developers
1
Foundations
WEEKS 1-8
Azure landing zone: AKS, Flexible Server, PgBouncer, Redis, Blob, Key Vault
Helm charts for all nine services
CI/CD to staging and production
Structured logs, OpenTelemetry, Prometheus, Grafana
Backups, PITR, first restore drill
Redis rate limiter
2
Control layer
WEEKS 9-16
Entra ID SSO, per-tenant IdP, token revocation
usage_events, async metering, rollups
Entitlements and hard quota enforcement
Service auth on internal endpoints
Admin console
Isolation and RBAC test suites
3
Capability plane
WEEKS 17-26
Protocols, registry, config-driven topology
LLM broker with budgets and queues
Golden-set harness and fixtures
Graph-RAG retriever
Chart agent
Multi-format ingestion
Hash-routed model cache, Celery queues, GPU pool
4
Hardening
WEEKS 27-34
Multi-zone HA, read replica, PDBs, probes
Load suite and the noisy-neighbour test
Performance remediation reserve
Chaos suite and graceful degradation
Security scanning and LLM Top 10
External pentest and remediation
Runbooks and on-call
5
Beta to GA
WEEKS 35-40+
Internal alpha, 4 weeks
Closed beta, 2-3 clients, 8 weeks
GA exit criteria met
Pricing, licensing, branding and multi-region enter planning as separate workstreams
Sequencing rationale. Observability before optimisation — you cannot fix contention you cannot measure. Metering before the LLM broker, because budgets need a meter. Both before load testing.

## Slide 16
INFRASTRUCTURE COST
Roughly $1.9-2.6k per month at 10-15 tenants
Chart: 
| Postgres HA | AKS app pool | AKS memory pool | Azure OpenAI (mid) | Read replica | Log Analytics + KV | Redis | Blob + backup | Front Door + WAF | GPU spot | Registry
USD per month | 520 | 420 | 290 | 550 | 140 | 90 | 75 | 45 | 45 | 30 | 20
What to note
Reserved instances cut compute 30-40%
Always-on staging adds ~$400 — recommended, and cheaper than testing in production
Reservations plus scheduled staging shutdown brings fixed cost to ~$1,100
The GPU line
No GPU budget was allocated, but spot T4 capacity at $0.15-0.30/hour makes on-demand training about $30 per month at expected volume. The CPU-only fallback saves that $30 and costs 4-8 hours of wall clock per training job — which becomes the bottleneck in the annotate, train, evaluate loop tenants depend on.
Recommendation: approve the GPU line.
Azure list prices, Central India, single region. LLM spend is the only line that scales with tenants — which is why it is metered per tenant from day one.

## Slide 17
RISKS AND WHAT WE NEED FROM YOU
The real risk is team capacity
Top risks
Three junior developers doing Azure, Kubernetes, OpenTelemetry, SSO and a security programme at once — the dominant risk. Mitigation: buy managed services everywhere, phase strictly, consider a part-time DevOps contractor for Phase 1
No QA or security resource — automated blocking gates are the substitute
Existing chatbots are undocumented; owner availability is a scheduling dependency, not an assumption
NER model quality (open issue on v8) caps answer quality. Out of scope by decision, but tracked visibly
Azure OpenAI TPM quota lead times — request the increase early
To start Phase 1
Azure subscription and region confirmed
Approve the GPU spot line (~$30/month)
Always-on staging: yes or no
Confirm Azure OpenAI as the sanctioned provider
By Phase 3
Owner contact for each existing chatbot
File formats actually required, in priority order
By Phase 5
Pricing · SLA · Beta cohort · Compliance target
Full plan: docs/production-plan.md
Notes: Ask for approval on the four Phase 1 decisions today; the rest can follow the phase schedule.